## Features
Project: Booking Hotel
Team: 20
ID | Feature Name | Description | Remark
UC01 | Authentication | All users can sign up with proper personal information and be able to sign in using the signed-up details
UC02 | Hotel rooms management | Hotel owner can add their rooms and edit their rooms information and details
UC03 | Customer booking management | Customer can book rooms of choice, cancel their booking that has not completed, and be able to add reviews to their past bookings
UC04 | Valid form for search | Customer can search for rooms with search details: Location, Start date, end date, amout of people, amount of room
UC05 | System and rendering | the complete page is rendered and displayed correctly on the desktop per the design specifications.
UC06 | Update profile | User can update their profile with valid personal information
UC06 | User profile | User can update their profile with valid personal information

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01: Authentication
UC01 | UI01 | Login with valid email and password | 1. Click "Sign In" on navigation bar 2. Enter email: "testuser@gmail.com" 3. Enter password: "tester" 4. Click "Sign In" | 1. User authenticated 2. Navigation bar display user avatar | 1. User authenticated 2. Navigation bar display user avatar | Passed | NTATuyet | 07/01/23
UC01 | UI02 | Login with valid email and invalid password | 1. Click "Sign In" on navigation bar 2. Enter email: "testuser@gmail.com" 3. Enter password: "tester123" 4. Click "Sign In" | 1. System displays "Wrong password" message 2. User not authenticated | 1. System displays "Wrong password" message 2. User not authenticated | Passed | NTATuyet | 07/01/23
UC01 | UI03 | Login with invalid email and valid password | 1. Click "Sign In" on navigation bar 2. Enter email: "testuser123@gmail.com" 3. Enter password: "tester" 4. Click "Sign In" | 1. System displays "Email not found" message 2. User not authenticated | 1. System displays "Email not found" message 2. User not authenticated | Passed | NTATuyet | 07/01/23
UC01 | UI04 | Login with invalid email and invalid password | 1. Click "Sign In" on navigation bar 2. Enter email: "testuser123@gmail.com" 3. Enter password: "tester123" 4. Click "Sign In" | 1. System displays "Email not found" message 2. User not authenticated | 1. System displays "Email not found" message 2. User not authenticated | Passed | NTATuyet | 07/01/23
UC01 | UI05 | Create customer account with valid information | 1. Click "Sign Up" on navigation bar 2. Fill in valid username and password 3. Fill in valid phone number, email, and id card number 4. Choose "Customer" in account type 5. Accept terms & conditions 6. Click "Sign Up" | 1. User redirected to homepage 2. Navigation bar shows default logged in avatar | 1. User redirected to homepage 2. Navigation bar shows default logged in avatar | Passed | NTATuyet | 07/01/23
UC01 | UI06 | Create hotel owner account with valid information | 1. Click "Sign Up" on navigation bar 2. Fill in valid username and password 3. Fill in valid phone number, email, and id card number 4. Choose "Hotel Owner" in account type 5. Accept terms & conditions 6. Click "Sign Up" | 1. User redirected to homepage 2. Navigation bar shows default logged in avatar | 1. User redirected to homepage 2. Navigation bar shows default logged in avatar | Passed | NTATuyet | 07/01/23
UC01 | UI07 | Create customer account with used email | 1. Click "Sign Up" on navigation bar 2. Fill in valid username and password 3. Fill in valid phone number, email is "testuser@gmail.com", and id card number 4. Choose "Customer" in account type 5. Accept terms & conditions 6. Click "Sign Up" | 1. System displays "Email is already in use" message 2. User not signed up | 1. System displays "Email is already in use" message 2. User not signed up | Passed | NTATuyet | 07/01/23
Function 02: Hotel rooms management
UC02 | UI01 | Hotel owner create a new room | 1. Click "Create New Room" in hotel owner dashboard 2. Upload room images 3. Fill in room details and facilities 4. Add rooms with pricing information 5. Click "Create room" | 1. System displays "Create room successful" 2. Room created | 1. System displays "Create room successful" 2. Room created | Passed | NTATuyet | 07/01/23
UC02 | UI02 | Hotel owner create a new room with missing information | 1. Click "Create New Room" in hotel owner dashboard 2. Upload room images 3. Click "Create room" | 1. System shows "The field is required" in data fields 2. Room not created | 1. System shows "The field is required" in data fields 2. Room not created | Passed | NTATuyet | 07/01/23
UC02 | UI03 | Hotel owner add a room type to the hotel | 1. Click "See more" of the room in hotel owner dashboard 2. Click "Add room" 3. Fill in room information 4. Click "Save changes" | 1. System shows "Update rooms successful 2. Room type added to the room | 1. System shows "Update rooms successful 2. Room type added to the room | Passed | NTATuyet | 07/01/23
UC02 | UI04 | Hotel owner add a room type to the hotel with no information | 1. Click "See more" of the room in hotel owner dashboard 2. Click "Add room" 3. Click "Save changes" | 1. System shows "Field is required" in missing fields 2. Room type not added to the room | 1. System shows "Field is required" in missing fields 2. Room type not added to the room | Passed | NTATuyet | 07/01/23
UC02 | UI05 | Hotel owner remove a room type to the hotel | 1. Click "See more" of the room in hotel owner dashboard 2. Click delete button of the room type 3. Click "Save changes" | 1. System shows "Update rooms successful 2. Room type removed | 1. System shows "Update rooms successful 2. Room type removed | Passed | NTATuyet | 07/01/23
UC02 | UI06 | Hotel owner edit a room details | 1. Click "See more" of the room in hotel owner dashboard 2. Edit details of the room 3. Click "Save changes" | 1. System shows "Update rooms successful 2. Room details updated | 1. System shows "Update rooms successful 2. Room details updated | Passed | NTATuyet | 07/01/23
UC2 | UI07 | Redirect to Dashboard after manage | 1. Go to dashboard and click "Create new room" 2. Fill in room information and images 3. Click create room | 1. System displays "Create room success" 2. User redirected to dashboard with room created | 1. System displays "Create room success" 2. User redirected to dashboard with room created | Passed | NTLuc | 12/01/23
UC2 | UI08 | Hotel owner can create multiple rooms if they click create room mutlple times | 1. Go to dashboard and click "Create new room" 2. Fill in room information and images 3. Click "create room" 4. Click "create room" 5. Click "create room" | 1. System displays "Create room success" 2. User redirected to dashboard with room created once | 1. System displays "Create room success" 2. User redirected to dashboard with room created three times | Failed | NTATuyet | 07/01/23
UC2 | UI09 | Dashboard without total revenue and total customer | 1. Customer reserve a room of hotel owner 2. Hotel owner go to dashboard 3. See total revenue and total customer of hotel | Total revenue and total customer displayed on dashboard page | Total revenue and total customer have not been updated on dashboard page | Failed | NTLuc | 12/01/23
Function 03: Customer booking management
UC03 | UI01 | Customer book a room | 1. Click "See more" of the room 2. Select booking date range 3. Select quantities of each room types 4. Click "Book now" | 1. System shows "Book successful" 2. Booking show up in "Recent booking" | 1. System shows "Book successful" 2. Booking show up in "Recent booking" | Passed | NTATuyet | 07/01/23
UC03 | UI02 | Customer book a room with coupon code | 1. Click "See more" of the room 2. Select booking date range 3. Select quantities of each room types 4. Select a coupon code 5. Click "Book now" | 1. System shows "Book successful" 2. Booking show up in "Recent booking" with reduced price | 1. System shows "Book successful" 2. Booking show up in "Recent booking" with undiscounted price | Passed | NTATuyet | 07/01/23
UC03 | UI03 | Customer add a review to their past booking | 1. Click "Add review" on the past booking 2. Select rating from 1-5 and add details to the review 3. Add images to the review 4. Click "Send Review" | 1. System shows "Add review successful" 2. "Add review" button replaced by "Reviewed" 3. Review added to the room | 1. System shows "Add review successful" 2. "Add review" button replaced by "Reviewed" 3. Review added to the room | Passed | NTATuyet | 07/01/23
UC03 | UI03 | Customer add a review with missing information | 1. Click "Add review" on the past booking 2. Click "Send Review" | 1. System shows "Field is required" at missing fields 2. Review not added | 1. System shows "Field is required" at missing fields 2. Review not added | Passed | NTATuyet | 07/01/23
Function 04: Valid form for search
UC04 | UI01 | Search with a valid "From" date | 1. Pick valid "From" date: Eg: "31/01/2023" 2. Pick valid "To" date: "01/02/2023" 3. Click "Search" on search form | 1. Display search result page | Same with ER | Passed | NTLuc | 12/01/23
UC04 | UI02 | Search with a invalid "From" date in date picker field - Eg: From date greater than "to" date | 1. Pick valid "To" date: "15/01/2023" 2. Pick invalid "From" date: "16/01/2023" | 1. System prevent user pick invalid "From" date 2. Customer must pick "From" date equal today or less than "To" date 3. Display search result page | Same with ER | Passed | NTLuc | 12/01/23
UC04 | UI03 | Search with a valid "To" date | 1. Pick valid "To" date: "15/01/2023" 2. Pick valid "From" date: "16/01/2023" 3. Click "Search" on search form | 1. Display search result page | Same with ER | Passed | NTLuc | 12/01/23
UC04 | UI04 | Search with a invalid "To" date | 1. Pick valid "From" date: "15/01/2023" 2. Pick invalid "To" date: "14/01/2023" | 1. System prevent user pick invalid "To" date 2. Customer must pick "To" date equal or greater than "From" date 3. Display search result page | Same with ER | Passed | NTLuc | 12/01/23
UC05 | UI05 | Save searching infomation | 1. Search on landing page with your infomation 2. Search infomation is saved | Search infomation: location, start date, end date, rooms and people saved on search result | Search information has not been saved | Failed | NTLuc | 12/01/23
Function 05: System and rendering
UC05 | UI01 | Check if user can access the landing page | 1. Login account 2. Access the landing page | 1. Disallows the user to proceed and 2. The error message should be displayed | 1. Allows the user to proceed and 2. The error message is not displayed | Passed | NTLuc | 12/01/23
UC05 | UI02 | Check if all page are rendered and displayed on the desktop corectly per the design specifications | 1. Login account 2. Access the landing page 3. Go to the search page 4. Go to the details page 5. Go to the account management page ... | All page displayed correctly same with the design specifications | All page displayed correctly same with the design specifications | Passed | NTLuc | 12/01/23
Function 06: User profile
UC06 | UI01 | User update their information | 1. Click "Profile" on the navigation bar 2. Edit user information 3. Click "Save changes" | 1. System displays "Update profile successful" 2. User profile updated | 1. System displays "Update profile successful" 2. User profile updated | Passed | NTATuyet | 07/01/23
UC06 | UI02 | User upload a new avatar | 1. Click "Profile" on the navigation bar 2. Click upload button and choose new avatar 3. Click "Save changes" | 1. System displays "Update profile successful" 2. User avatar updated | 1. System displays "Update profile successful" 2. User avatar updated | Passed | NTATuyet | 07/01/23
UC06 | UI04 | User update profile with missing information | 1. Click "Profile" on the navigation bar 2. Clear the username field (leave blank) 3. Click "Save changes" | 1. System displays "Username is required" 2. User username not updated | 1. System displays "Username is required" 2. User username not updated | Passed | NTATuyet | 07/01/23
UC06 | UI05 | User remove avatar | 1. Click "Profile" on the navigation bar 2. Click delete button on the avatar 3. Click "Save changes" | 1. System displays "Update profile successful" 2. User avatar change to default user avatar | 1. System displays "Update profile successful" 2. User avatar change to default user avatar | Passed | NTATuyet | 07/01/23